## Sheet1
SL # | Observations shared by | Name of the forms | Name of Action | Reported Date | Issue | Assigned to | Status | Remarks | Dev Remarks | PR
166 | Anup Singh | NPS Transaction Punching Interface | Modify Button | 11-Jan-2025 (B) | Allow only user to punch any transaction from punching form with punching Role Only. No other role should be allowed for punching any transaction (LI, GI, MF, FI, NPS)' | Shahnawaz | Not Fixed | Jan 25: In QA 24-Jan: PR Raised on 23-Jan Due to blocker unable to test form https://screenrec.com/share/k3iSwUXKDA | Not fixed: 17-01-2025 | 1905-01-23
167 | Anup Singh | NPS Transaction Punching Interface | Modify Button | 11-Jan-2025 (B) | while modifying transaction, scheme code is updated in backend as "0" zero DT - 40682328 | Shahnawaz | Not Fixed | Jan 25: In QA 24-Jan: PR Raised on 23-Jan Due to blocker unable to test form https://screenrec.com/share/k3iSwUXKDA | Not fixed: 17-01-2025 | 1905-01-23
168 | Anup Singh | NPS Transaction Punching Interface | Browser Back Button | 11-Jan-2025 (B) | While clicking back button of browser. Its again and showing updated successfully message | Shahnawaz | Not Fixed | Jan 25: In QA 24-Jan: PR Raised on 23-Jan Due to blocker unable to test form https://screenrec.com/share/k3iSwUXKDA | Not fixed: 17-01-2025 | 1905-01-23
172 | Anup Singh | NPS Transaction Punching Interface | Design Issues | 11-Jan-2025 (B) | Redesign Forms Fields as it data is hide due to it's conciseness | Shahnawaz | Not Fixed | Jan 25: In QA 24-Jan: PR Raised on 23-Jan Due to blocker unable to test form https://screenrec.com/share/lsUPzaSJ73 | Not fixed: 17-01-2025 | 1905-01-23
173 | Anup Singh | NPS Transaction Punching Interface |  | 11-Jan-2025 (B) | ECS Part new devlopment | Shahnawaz | WIP | Shahnawaz: 23 Jan 75 % Dev Done, Need sample file for importing in db
295 | Anup Singh | NPS Transaction Punching Interface |  | 2025-01-13 | EXIT CTA Button Navigation: After click on EXIT button user log-out from appliaction | Shahnawaz | Not Fixed | Jan 25: In QA 24-Jan: PR Raised on 23-Jan User should redirect onto dashboard of the application Not fixed - 31-01-2025 https://screenrec.com/share/dnk2t8zo6y | Navigation issue still not fixed: 27-01-2025 https://screenrec.com/share/HnscSfjlWz | 1905-01-23
305 | Anup Singh | NPS Transaction Punching Interface | Missing Pop-up | 2025-01-13 | Popu-up window should alert user before punching entry into system & display error validation for invalid entry submitted by user "Enter DT number then show pop-up" if exists otherwise display error validation to user: (i) Already punched (ii) Rejected DT number (iii) Invalid DT number | Shahnawaz | Need Clarification | fresh entry punching Restrict user from punching invalid entry into form | It should display pop-up after enter DT number on the form https://screenrec.com/share/9Jeols4gDB
317 | Anup Singh | NPS Transaction Punching Interface | Missing Pop-up | 2025-01-13 | "Search AR" need pop-up window 1. At the time of audit 2. After punching | Shahnawaz | Need Clarification | Display pop-up window to user with valid information | Prompt pop-up window to user after search AR on the form https://screenrec.com/share/Eud5vzSGI2
452 | Anup Singh | NPS Transaction Punching Interface |  | 2025-01-31 | "Search AR" pop-up window closed automatically after searching record, again click on search window to select record to fetch details on the form | Shahnawaz | Yet to be picked | https://screenrec.com/share/fI78m19Cj3
453 | Anup Singh | NPS Transaction Punching Interface | Fresh entry | 2025-01-31 | "No data in transaction st" unable to add fresh entry into the form DT number - 40685681 | Shahnawaz | Blocker | https://screenrec.com/share/k3iSwUXKDA
454 | Anup Singh | NPS Transaction Punching Interface | only 12 digits under PRAN No. | 2025-01-31 | "PRAN No." should accept only 12 digits neither > 12 nor <12 missing fields validation on search AR | Shahnawaz | Yet to be picked | https://screenrec.com/share/ae5AhK2ImL