## Sheet1
S.No. | Observations shared by | Name of the forms | Name of Action | Reported Date | Issue | Assigned to | Status | Remarks | Dev Remarks | PR
26 | Rahul | Account Opening |  | 11-Jan-2025 (B) | Screen flickering issue un updating the fields like pin code | Shahnawaz | Not Fixed | 15-Jan: Moved to Prod (Status changed by Amitava) top to bottom | Shahnawaz: 10 : Issue fixed flikering on pin adn also added pin validation, but coutnrym state flikering is still Need PR
34 | Anup Singh | Sub Broker Master | DT No Capturing Missing | 11-Jan-2025 (B) | Associate can not be created without DT No | Shahnawaz | Not Fixed | 7-Feb: In QA DT captured but still issue exists, If DT already punched & asscociated code is generated in system , It should give Exist code & proper message to user i.e. DT no. Already punched DT Number - 603446958 https://screenrec.com/share/sKJa1OjqAT | 12-Dec: PR Raised, Build merged & published Not fixed - 17-01-2025 It should Display searched DT to user Column 'DT_NUMBER' does not belong to table . Not fixed - 08-02-2025 No data found https://screenrec.com/share/qQ2trPmYa0 | 2025-02-03
35 | Anup Singh | Sub Broker Master | Select Employee | 11-Jan-2025 (B) | Employee Names are not getting populated after selecting branch name Note: Branch and Employee should be filled automatically after entering DT No | Shahnawaz | Not Fixed | 7-Feb: In QA Not fixed: This is according to upload data by RM & this should be non-editable 17-01-2025 | 12-Dec: PR Raised, Build merged & published Not fixed - 17-01-2025 Still editable | 2025-02-03
37 | Anup Singh | Sub Broker Master | Address line 2 and 3 Missing | 11-Jan-2025 (B) | Address line missing for user | Shahnawaz | Not Fixed | 7-Feb: In QA Still address not visible https://screenrec.com/share/8P1Fawjm4Q | 12-Dec: PR Raised, Build merged & published Not fixed - 17-01-2025 Missing Address line 3 | 2025-02-03
38 | Anup Singh | Sub Broker Master | Residence Address Button | 11-Jan-2025 (B) | Functionality Missing not able to perform any actions | Shahnawaz | Not Fixed | 7-Feb: In QA Still not fixed https://screenrec.com/share/MuUHXcSdAE | 12-Dec: PR Raised, Build merged & published Not fixed - 17-01-2025 There is no button visible to click | 2025-02-03
39 | Anup Singh | Sub Broker Master | Search Super ANA | 11-Jan-2025 (B) | Blocker: Super ANA Search Not Working....many search parameters are missing | Shahnawaz | Not Fixed | 7-Feb: In QA Grid not working properly selected items not display under grid https://screenrec.com/share/iEauXJm10A Missing functionality grid missing https://screenrec.com/share/GbPvtCSNsq | 12-Dec: PR Raised, Build merged & published Not fixed - 17-01-2025 | 2025-02-03
40 | Anup Singh | Sub Broker Master | Audited section not required | 11-Jan-2025 (B) | Should be autofilled from DMS Audit window | Shahnawaz | Not Fixed | 7-Feb: In QA We are not able to proceed further due to blocker https://screenrec.com/share/U29FBNhGQX | 12-Dec: PR Raised, Build merged & published Not fixed - 17-01-2025 Still Audit section visible | 2025-02-03
42 | Anup Singh | Sub Broker Master | Add Button | 11-Jan-2025 (B) | Most of the validation not working. Got the message "Record Added Successfully" but no data validated. Just Name Branch and Super ANA asked after that nothing entered and Agent Created | Shahnawaz | Not Fixed | 7-Feb: In QA Still blocker unable to proceed further Not fixed - https://screenrec.com/share/GbPvtCSNsq | 12-Dec: PR Raised, Build merged & published | 2025-02-03
47 | Anup Singh | ANA MERGING | Missing branches | 11-Jan-2025 (B) | ALL BRANCHES SHOULD NOT DISPLAY AND INACTIVE BRANCH SHOULD NOT DISPLAY | Shahnawaz | Not Fixed | Blocker: Branches not displaying to perform any action https://screenrec.com/share/yjrcIgD3uT | Not fixed - 17-01-2025 There is no branch to show in list Not working unable to proceed further
49 | Anup Singh | ANA MERGING | Agent search popup missing part development | 11-Jan-2025 (B) | Agent search popup missing part development | Shahnawaz | Not Fixed | 09-Jan-2025 13:11 HRs: Build published in UAT No pop-up will sown on the form | Not fixed - 17-01-2025
53 | Anup Singh | Sub Broker Master | Search | 11-Jan-2025 (B) | Issue in searching not able to fetch record on the form to perform action | Shahnawaz | Not Fixed | 7-Feb: In QA Live: https://screenrec.com/share/PTpRkXgCsv Not fixed - https://screenrec.com/share/A6NlM2RGch | Not fixed: 17-01-2025 | 2025-02-03
54 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | Blocker: Column 'DT_NUMBER' does not belong to table | Shahnawaz | Not Fixed | 7-Feb: In QA https://screenrec.com/share/zlEZWdgi27 | Not fixed: 17-01-2025 | 2025-02-03
55 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | Rejected DT Numbers should not fetch data on the form | Shahnawaz | Not Fixed | 7-Feb: In QA https://screenrec.com/share/fTkvGqHQz1 | Not fixed: 17-01-2025 | 2025-02-03
56 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | Filter not working for branches all branches visbile to user | Shahnawaz | Not Fixed | 7-Feb: In QA Related branches should be shown to user | Not fixed: 17-01-2025 | 2025-02-03
166 | Anup Singh | NPS Transaction Punching Interface | Modify Button | 11-Jan-2025 (B) | Allow only user to punch any transaction from punching form with punching Role Only. No other role should be allowed for punching any transaction (LI, GI, MF, FI, NPS)' | Shahnawaz | Not Fixed | Jan 25: In QA 24-Jan: PR Raised on 23-Jan Due to blocker unable to test form https://screenrec.com/share/k3iSwUXKDA | Not fixed: 17-01-2025 | 1905-01-23
167 | Anup Singh | NPS Transaction Punching Interface | Modify Button | 11-Jan-2025 (B) | while modifying transaction, scheme code is updated in backend as "0" zero DT - 40682328 | Shahnawaz | Not Fixed | Jan 25: In QA 24-Jan: PR Raised on 23-Jan Due to blocker unable to test form https://screenrec.com/share/k3iSwUXKDA | Not fixed: 17-01-2025 | 1905-01-23
168 | Anup Singh | NPS Transaction Punching Interface | Browser Back Button | 11-Jan-2025 (B) | While clicking back button of browser. Its again and showing updated successfully message | Shahnawaz | Not Fixed | Jan 25: In QA 24-Jan: PR Raised on 23-Jan Due to blocker unable to test form https://screenrec.com/share/k3iSwUXKDA | Not fixed: 17-01-2025 | 1905-01-23
172 | Anup Singh | NPS Transaction Punching Interface | Design Issues | 11-Jan-2025 (B) | Redesign Forms Fields as it data is hide due to it's conciseness | Shahnawaz | Not Fixed | Jan 25: In QA 24-Jan: PR Raised on 23-Jan Due to blocker unable to test form https://screenrec.com/share/lsUPzaSJ73 | Not fixed: 17-01-2025 | 1905-01-23
228 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | Only ANG channel should be visible under branch drop down list | Shahnawaz | Not Fixed | 7-Feb: In QA https://screenrec.com/share/tBRGN1hka9 | Not fixed: 17-01-2025 Still all branches displaying | 2025-02-03
229 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | City > Data not filtered for selection i.e. random data shown | Shahnawaz | Not Fixed | 7-Feb: In QA https://screenrec.com/share/eQqFuC7gA9 | Not fixed: 17-01-2025 | 2025-02-03
230 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | Mobile number should start from "6789" If already exists in system (Agent Master Table) then it should stop user & give proper error message, User should not proceed further | Shahnawaz | Not Fixed | 7-Feb: In QA https://screenrec.com/share/uQCPSnUqeL |  | 2025-02-03
231 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | Error validation shown for Duplicate "Email" & "Mobile", "PAN Number" fields | Shahnawaz | Not Fixed | 7-Feb: In QA |  | 2025-02-03
232 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | Contact Person Email ID should automatically populate from Email ID | Shahnawaz | Not Fixed | 7-Feb: In QA It should auto fetch after enter DT number on the form https://screenrec.com/share/KU3fgTkJRH |  | 2025-02-03
233 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | "Source" should be in name not in number Not responding | Shahnawaz | Not Fixed | 7-Feb: In QA Not working https://screenrec.com/share/89nI5xGpLX |  | 2025-02-03
234 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | Bank Details should automatically fetch | Shahnawaz | Not Fixed | 7-Feb: In QA https://screenrec.com/share/ZSROMKcyu5 |  | 2025-02-03
235 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | There is no seprate NEFT details in old interface, Add under Bank details section | Shahnawaz | Not Fixed | 7-Feb: In QA |  | 2025-02-03
236 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | Area Branch> Not able to select branch "Select branch first" | Shahnawaz | Not Fixed | 7-Feb: In QA Blank list under Area https://screenrec.com/share/LrTofJYISi |  | 2025-02-03
237 | Anup Singh | Sub Broker Master |  | 11-Jan-2025 (B) | For Other country numeric value should allow | Shahnawaz | Not Fixed | 7-Feb: In QA |  | 2025-02-03
295 | Anup Singh | NPS Transaction Punching Interface |  | 2025-01-13 | EXIT CTA Button Navigation: After click on EXIT button user log-out from appliaction | Shahnawaz | Not Fixed | Jan 25: In QA 24-Jan: PR Raised on 23-Jan User should redirect onto dashboard of the application Not fixed - 31-01-2025 https://screenrec.com/share/dnk2t8zo6y | Navigation issue still not fixed: 27-01-2025 https://screenrec.com/share/HnscSfjlWz | 1905-01-23
398 | Anup Singh | Account Opening | Design issue | 2025-01-22 | Design Issue: Date picker not aligned on the form under "Investor Details" | Shahnawaz | Not Fixed | https://screenrec.com/share/bG50ikEZQV Not fixed - 29-01-2025 https://screenrec.com/share/Ghs9eEunFd Re-Open 07-02-2025 https://screenrec.com/share/j3WYKgoF2J | once the date picked open choose a date or cliek else where it is simple,
401 | Anup Singh | Account Opening | Incorrect data fetching | 2025-01-22 | (Other Details) > Incorrect data fetching after choosing investor from list, Ex: If we select newly created investor then data of existing investor is fetch on the form Client Code - AH618017 | Shahnawaz | Not Fixed | 7-Feb: In QA https://screenrec.com/share/M6RTfaHmVr Not fixed - 29-01-2025 https://screenrec.com/share/qIK8cdfYZm Re-Open 07-02-2025 https://screenrec.com/share/WbpyaUhPVl | It is fetchign data on the bases of the inv code and in database, the data of that client mismatch thats why. afterall functionality is totaly correct | 2025-02-03
418 | Anup Singh | Account Opening | design issue: | 2025-01-30 | Design issue: client/Invetor search window not aligned on the form | Shahnawaz | Not Fixed | 7-Feb: In QA https://screenrec.com/share/mTFcwRbheu Re-Open 07-02-2025 https://screenrec.com/share/j3WYKgoF2J |  | 2025-02-03
421 | Anup Singh | Account Opening | screen flickering | 2025-01-30 | Screen flickering issue still not resolved on the form | Shahnawaz | Not Fixed | https://screenrec.com/share/iGohLHPtFn